Capture following outputs to save configuration

sysconfig

fcadmin config

disk show –v

storage show adapter

storage show disk –p

sysconfig –a

sysconfig –r

aggr status

vol status

sp status

version –b

rdfile /etc/rc

vfiler run * exportfs

vfiler run * cifs shares

vfiler run * iscsi nodename

vfiler run * igroup show

vfiler run * lun serial

vfiler run * lun show –v

vfiler run * vfiler status -a

## Controller Preparation

Estimated time for completion:

2 hours

Estimated user outage:

None required

Additional Resources:

Console access to filers

Procedures:

Copy the 8.1.3P3 binaries for the 3250AE to the /etc/software directory on the source controllers (and stage netboot files on an HTTP server)

Copy the disk firmware update binaries to the /etc/software directory on both source controllers

Copy the shelf firmware update binaries to the /etc/software directory on both source controllers

Copy the service processor firmware update binaries to the /etc/software directory on both source controllers

Copy the disk qualification binaries (V3) to the /etc/software directory on both controllers

Create a historical data point

options autosupport.doit “Pre-Headswap”

Disable AutoSupport to prevent over-messaging (wait 5 minutes and ensure “LAS Vegas Casino Alert Sounds” occur.

options autosupport.enable off

options autosupport.support.enable off

Verify the disk ownership to see if the ownership of the disks is mixed in the loop.

Example (Do all disks in a single loop belong to the same controller?)

Identify the iSCSI and FCP nodename as applicable for all VFilers (capture)

fcp show nodename

iscsi nodename

vfiler run * iscsi nodename

Verify LUNs and serial numbers (capture)

lun show –v

vfiler run * lun show -v

Disable Cluster Failover

cf disable

## Upgrade Procedures

Estimated time for completion:

4 hours (V3270 to FAS3250 Head Upgrade/Re-Cable)

Additional Resources:

Console access to filers

Power screwdriver / drill

Procedures:

Modify the /etc/rc on both controllers to reflect new network port slots if applicable

Shutdown both nodes

vfiler run * cifs terminate

halt

Remove the V3270s from the cabinet while ensuring all cables are labeled for re-connection

Reconfigure disk shelves according to agreed cabling scheme

Install the FAS3250AE in the cabinets

Connect power cables to controllers and disk shelves appropriately

Connect network cables to controllers appropriately

Connect the SAS “A” loops to the controllers

Boot one Controller at a time to LOADER prompt

‘<ctrl> c’ to stop autoboot

printenv

set-defaults

printenv

setenv partner-sysid <partner_sysid>

printenv partner-sysid

ifconfig e0a –addr=<address> -mask=<netmask> -gw=<gateway>

netboot http://<address of web server>/813P3_netboot.tgz

OR

boot_ontap

Boot into maintenance mode (option 5)

Make sure that the correct ports are set to target

Ensure the appropriate ports are target ports

fcadmin config

fcadmin config –t target 0c

fcadmin config –t target 0d

Reboot the controllers back into Maintenance Mode and verify the ports are still configured

fcadmin config

If they are set as expected then continue

Once backend storage array changes are complete, reboot the NetApp FAS controller and boot back into maintenance mode

Verify that you can see all the disks

disk show –v

Look at the beginning of the output to capture the sys_id for that controller.  That will be needed to reassign the disks

On each controller reassign the disk ownership from the old controller to the new controller

For the controller with hostname of HOSTNAME1

disk reassign –s OLD-SERIAL –d NEW-SERIAL

For the controller with hostname of HOSTNAME2

disk reassign –s OLD-SERIAL –d NEW-SERIAL

Verify disk assignments

disk show –v

Verify disk paths

storage show disk –p

Verify HA on new controler

Ha-config show

If not in HA mode, perform:

ha-config modify chassis ha

ha-config modify controller ha

On each controller clear the mailbox contents by entering the following commands:

mailbox destroy local

mailbox destroy partner

Verify all aggregates and RAID groups are present and complete

aggr status -r

halt

NetBoot Data ONTAP

ifconfig e0a –addr=<address> -mask=<netmask> -gw=<gateway>

netboot http://<address of web server>/813P3_netboot.tgz

- OR

Boot from Data ONTAP image on Compact flash if major version matches

boot_ontap

Watch the boot process and look for any errors

- Install all applicable licenses

- Note: Do not reboot at this time for the Licenses to take effect

On one controller at a time install Data ONTAP 8.1.3P3 by entering the following commands:

software list

software update 813P3_setup_q.tgz -r

download

reboot

Verify that the serial number of the LUNS did not change and are online

lun show –v

## Post-Upgrade Procedures

Estimated time for completion:

1 hour

Estimated user outage:

None Required

Additional Resources:

Network Admin to configure switch ports and verify connections

Procedures:

Compare sysconfig -a, sysconfig -r, aggr status and vol status output with the output displayed during the previous section to confirm that everything is normal

Enable Clustering

cf enable

Proceed with Verification Test Procedures in next section

Test the V6280A to ensure that everything has been configured correctly. The test needs to include; path failover tests, simulate switch outage, cluster takeover and giveback. Follow the installation checklist to test if the installation is proper.

On each controller configure the SP if it is to continue being used

sp status

sp setup

Enable AutoSupport

options autosupport.enable on

options autosupport.support.enable on

Send ASUPs to capture historical data

options autosupport.doit “Post-Headswap”

Connect ACP cables to controllers and disk shelves appropriately

Verify ACP connectivity and configuration

options acp